## Defect Log
Defect ID | Title | Severity | Type | Affected Module | Found By | Reproduction Steps | Expected Result | Actual Result | Status | Resolution | Evidence
DEF-01 | Parallel identical submissions create duplicate complaints | High | Application | Complaints (also visitors, service requests, SOS, deliveries, mess feedback) | NFT-21 (pytest, first run) | Log in as a student; send the same complaint 5 times in parallel (simulated double-click / flaky network). | One complaint stored; the other requests get 409 Conflict. | All 5 requests returned 201 and 5 identical complaints were stored (check-then-insert race). | Fixed | Added a per-user PostgreSQL advisory lock (services.lock_for_user) around duplicate checks in every create endpoint. Retest NFT-21: 1 x 201 + 4 x 409, 1 record stored. | test-results/run1-initial/pytest-junit.xml
DEF-02 | Visitors page scrolls sideways on a 375 px phone screen | Medium | Application | Visitors (UI layout) | NFT-18 (Playwright, first run) | Log in as a student on a 375 x 812 viewport and open Visitors. | No horizontal scrolling; tables scroll inside their card. | Page width 503 px > 375 px viewport; whole page scrolled horizontally. | Fixed | Cards inside CSS grids now use min-width: 0 so wide tables scroll within the card. Retest NFT-18: no overflow on 8 pages x 3 widths. | test-results/run1-initial/playwright-results.json
DEF-03 | Database connections exhausted at 300 concurrent users | High | Application / configuration | Backend database layer | NFT-02 (k6, first run) | Run k6 with 300 virtual users against the API started with 2 workers. | Error rate < 0.5 %, average < 3 s. | 0.82 % failed requests, p99 32 s. Log: 'remaining connection slots are reserved' and 'QueuePool limit ... timed out' – 2 workers x 50 pooled connections exceeded PostgreSQL max_connections (100). | Fixed | Pool made configurable (DB_POOL_SIZE / DB_MAX_OVERFLOW / DB_POOL_TIMEOUT) with defaults sized to the 40-thread request pool (35 + 5 per worker). An intermediate setting (10 + 5) caused 7 % pool time-outs and was rejected. Retest at 300 users: 0 % errors, average 1.4 s. | test-results/run1-initial/k6-peak-300vus.json
DEF-04 | Personal data is not encrypted at rest (NFR06) | Medium | Application (requirement gap) | Data storage | NFT-34 | Inspect the users and visitor_requests tables in PostgreSQL. | Personal data (phone, registration number, visitor details) encrypted in storage. | Passwords and OTPs are bcrypt-hashed, but phone numbers, registration numbers and visitor phone numbers are plain text. | Open | Planned: column-level encryption (pgcrypto or application-side Fernet) for PII, plus a managed database with encryption at rest and TLS (sslmode=require). | test-results/nft-results.json
DEF-05 | Response time grows about 21x from 50 to 300 concurrent users | Medium | Capacity | Whole system (single 2-vCPU host) | NFT-06 (k6) | Run k6 at 50, 150 and 300 users on the same 2-vCPU machine that also runs PostgreSQL and the load generator. | No significant degradation (p95 at 300 users <= 2 x p95 at 50 users). | p95 92 ms at 50 users vs 1,921 ms at 300 users; throughput levels off at about 162 requests/s (CPU-bound). Still within the 3 s average target. | Open | Re-test on production-sized hosting; scale horizontally (more workers/instances), cache dashboard counts, move the load generator off the server. | test-results/perf/k6-*.json
DEF-06 | Firefox and WebKit (Safari) could not be tested in this environment | Low | Test environment | Compatibility testing | NFT-27, NFT-28 | Run 'ALL_BROWSERS=1 npx playwright test'. | Smoke test runs in Firefox and WebKit. | browserType.launch: Executable doesn't exist – the sandbox network policy blocks the Playwright browser downloads. | Open (blocked) | On a normal machine run 'npx playwright install firefox webkit' then 'npm run test:all-browsers' in e2e/. | test-results/playwright-results.json
DEF-07 | Test-script defects found while running the suites | Low | Test script | Automated tests | First runs: NFT-23 (pytest); FT-06, FT-08, FT-30, NFT-10, NFT-16, NFT-17 (Playwright) | (a) NFT-23 checked audit entries created by tests that run later; (b) E2E locators such as getByLabel('Category') also matched filter/search inputs; (c) a CSS selector used a React id containing ':'; (d) a Tab key press happened before the page rendered; (e) run_all_tests.sh stored the PID of a wrapper shell instead of the load-test server, so the server kept running and later exhausted PostgreSQL connections (HTTP 500 in the NFT runner). | Tests independent of order and with unambiguous selectors. | 7 false failures in the first runs (1 pytest, 6 Playwright), 3 more while fixing selectors, and one aborted pipeline run (e) – none were application defects. | Fixed | NFT-23 now performs its own actions; E2E tests use name-based selectors and wait for rendering; the pipeline starts the server with 'exec' and waits for the port to close. All affected tests were re-run with the complete pipeline. | test-results/run1-initial/
DEF-08 | Status filter drop-down stretched across card headers | Low | Application | UI components (Visitors, Services, SOS, Gate desk) | Manual visual review of screenshots (not detected by automated tests) | Log in as a warden and open Visitors. | Card title on the left, compact filter on the right. | The filter used the full-width input style, so it filled the header and wrapped the card title onto two lines. | Fixed | FilterSelect now has its own auto-width style. Frontend unit tests and the full Playwright suite were re-run afterwards. | docs/screenshots/11-warden-visitor-approvals.png
DEF-09 | Login fails with HTTP 500 when running on the built-in SQLite database | High | Application | Authentication / data layer | User report – local run on Windows with SQLite (not covered: automated suites used PostgreSQL) | Start the app without DATABASE_URL (SQLite file), log in once, then log in again. | Login succeeds. | TypeError: can't compare offset-naive and offset-aware datetimes in auth.login – SQLite returns dates without a time zone. | Fixed | All date/time columns now use a UTCDateTime type that always returns time-zone-aware UTC values. Re-tested: backend suite 60/61 and browser suite 23/23 on SQLite (the remaining SQLite case is the PostgreSQL-only parallel-submit lock, NFT-21); 61/61 and 23/23 on PostgreSQL. | backend/app/models.py (UTCDateTime)